## Sheet1
Team name: We_cant_think_of_a_name
Current sprint User Stories are in yellow
Issue # | Task Title | User Story | Story Points (out of 5) | Description / Associated Tasks | Due Date | Priority Level (LOW, MEDIUM, HIGH) | Risk Level (LOW, MEDIUM, HIGH) | Responsibles | Sprint
#8 | Setup database for professor credentials | "As an instructor, I want my email and password to be stored securely" | 4 | - Set up AtlasDB so that database is stored online via Mongoose - Add proof of concept code that can upload new users to database (with encryption) - Test everything on a terminal before linking to rest of the project | 2024-09-26 | HIGH | HIGH | Robert & Othmane | 1
#54 | Backend and Frontend merge in dev |  | 1 | On GitHub |  | MEDIUM | LOW | Hendrik | 1
#11 | Implement authentication procedure | "As a user, I want to log in with an extra sense of security" | 3 | - Validate student credentials (id & password) against database - Validate instructor credentials (email & password) against database. - Ensure that students are redirected to their specific dashboard upon successful login - Ensure that students are redirected to their specific dashboard upon successful login - Use encryption to store and compare passwords securely |  |  | HIGH | Robert & Jana & Yousef | 1
#9 | Design the student login page UI | "As a student, I want a clean, clear and visually appealing webstte where I will be able to log in to access the peer reviewing platform" | 2 | - HTML to create and place elements and form - CSS to add themes and colors and aesthetics - Javascript and React to make the page responsive - Ensure form is responsive | 2024-09-26 | HIGH | LOW | Elif & Jana | 1
#12 | Create session management for logged in users |  | 3 | - Implement sessions/tokens for student authentication - Implement sessions/tokens for instructor authentication | 2024-09-23 | HIGH | LOW |  | 2
#6 | Set up project |  | 1 | - Setting up tech stack - Set up gitignore - Set up file system & folder structure - Create README.md file - Set up issue tracking - Test repository set up | 2024-09-12 | HIGH | HIGH | Yousef & Elif | 1
#7 | Setup database for student credentials | "As a student, I want my email and password to be stored securely" | 4 | - Set up AtlasDB so that database is stored online via mongoose - Add proof of concept code that can upload new users to database (with encryption) - Test everything on a terminal before linking to rest of the project | 2024-09-26 | HIGH | HIGH | Robert & Othmane | 1
#13 | Invalid hook call error when adding React router |  | 2 | Issue faced: when adding router setup, app breaks and there is an error on F12 Console (warning: Invalid hook call. Hooks can only be called inside the body of a function component.) Help wanted. |  | LOW | LOW | Yousef & Hendrik & Jana | 1
#19 | Design instructor login page UI | "As an instructor, I want a clean, clear and visually appealing webstte where I will be able to log in to access the peer reviewing platform" | 2 | - HTML to create and place elements and form - CSS to add themes and colors and aesthetics - Javascript and React to make the page responsive - Ensure form is responsive | 2024-09-26 | HIGH | LOW | Elif & Jana | 1
#20 | Design student dashboard UI | "As a student, I want ot have an ovreview of the website on a single page so I can navigate where I wish" | 2 | - Create and place elements using HTML - Each course the student is taknig that requires peer reviewing appears on the website - Create API to get student data. - Map all student data to courses/teams they are part of |  | HIGH | LOW | Elif & Jana | 2
#21 | Design instructor dashboard UI | "As an instructor, I want ot have an ovreview of the website on a single page so I can navigate where I wish" | 2 | - HTML, CSS, Javascript, React - Implement sidebar - Overview of courses - Create new routes for API: creating course, adding students to course - Create model schemas for courses and teams - Add new functions to interact with database-API: create course and add student to course |  | HIGH | LOW | Elif & Jana | 2
#24 | Link website - server - database |  | 2 | There's a problem merging the branches, possibly because of our unfamiliarity with using MongoDB. Some changes and files don't appear after merge. |  | HIGH | MEDIUM | Robert & Youssef & Hendrik | 1
#27 | Merge what was done so far to main branch |  | 2 | On GitHub | 2024-09-30 | HIGH | LOW | Hendrik | 1
#28 | .env file to be removed from gitignore? |  |  | On GitHub |  |  |  | Hendrik
#29 | Team Management System | "As an instructor, I want to created the teams for the peer assessment manually" | 4 | - Create several new routes for the API: for getting the courses (instructor), for getting the students (instructor), for adding students to team (instructor) and for creating teams (instructor) and for displaying the existing teams (instructor). - GET /instructor/courses: Retrieve all courses that the instructor is teaching. @hendriktebeng - GET /instructor/courses/:courseId/students: Retrieve all students enrolled in a specific course. - POST /instructor/create-team: Create a new team by providing the team name, course ID, and selected student IDs. - POST /instructor/add-student-to-team: Add a student to an existing team. - GET /instructor/courses/:courseId/teams: Retrieve all teams created under a specific course. - Create model schemas for courses and teams. 1. Create Schema for Course Model: Fields: id: Unique identifier, courseCode: String, courseName: String, students: Array of student IDs, teams: Array of team IDs 2. Create Schema for Team Model: Fields: id: Unique identifier, teamName: String, course: Course ID , members: Array of students - Add new functions to interact with database-API: 1. createTeamForCourse(courseId, teamName, memberIds) : allows an instructor to manually create a team by providing the course ID, team name, and student IDs. 2. getAllCoursesForInstructor(instructorId): This function retrieves the list of courses assigned to a particular instructor. 3. getTeamsForCourse(courseId): This function retrieves all teams associated with a specific course. 4. addStudentToTeam(teamId, studentId): This function adds a student to an existing team by team ID and student ID. 5. getAvailableStudentsForCourse(courseId): This function retrieves all students in a course, excluding those already assigned to a team. 6. createCourse(courseCode, courseName, instructorId): This function allows the instructor to create a new course and store it in the database. 7. addStudentToCourse(courseId, studentId): This function adds a student to a course by course ID and student ID. ### **Front-End:** - Create page to interact with API. Course Management: 1. Display a dropdown to select a course. 2. Provide a form to create a new course by entering the course code and course name. Student Management 1. Display a multi-select box for the instructor to add students to the selected course. 2. Use API integration to update course-student relationships and reflect them in the UI. Create a team: Display a section for team creation with: 1. A textbox to enter the team name. @jana-madhoun 2. A multi-select box for selecting students (filtered by those not already in a team). Add members to a team: 1. Provide a form to add students to existing teams with dropdowns to select teams and students. | 2024-10-24 | HIGH | MEDIUM | Hendrik, Robert & Jana | 2
#30 | Peer Assessment UI | "As a student, I want to have an interface that allows me to pick teammates for evaluation, so that I can easily provide feedback to my peers during assessments" | 4 | Front End: - Design and Implement Interface: UI that lists teammates in a table format that displays the Name, Email and an Assessment Link that redirects to the peer assessment form for that student. - Selection and Redirection Functionality: Ensure that clicking on “Assess” redirects to the peer assessment form for the selected student. - Dynamic List Update: Ensure the table displays the latest list of teammates for evaluation. Back End: - Add new functions to interact with database-API: to create teams (instructor), to get all courses (instructor) and to get all created teams (instructor). - Database Operations: Teammates, teams, and assessments are properly stored and fetched from the database. - getTeammate(teammateId): Retrieve a teammate’s information. - getStudentTeammates(studentId): Fetch teammates for the logged-in student. - submitAssessment(evaluatorId, evaluateeId, assessment): Create a new peer assessment. - submitAssessments(evaluatorId, assessments): Submit multiple assessments for different teammates. API: Create the following routes: - GET /student-teammates returns a list of teammates with all required data. - POST /submit-assessment correctly saves individual assessments. - POST /login authenticates students and returns the appropriate user data. - GET /course-students/:courseId Retrieve students enrolled in a specific course by courseId. | 2024-10-25 | HIGH | MEDIUM | Elif, Robert & Hendrik | 2
#36 | 7-Point Peer-Assessment Scale | "As a student, I want to provide peer ratings using a 7-point scale for multiple assessment criteria and submit my evaluation, so that I can offer feedback to my peers." | 3 | - Create model schemas for assessments. - Create database functions to store assessments - Create an invididual assessment page to allow students to submit peer evaluation | 2024-10-26 | HIGH | MEDIUM | Hendrik, Robert & Jana | 2
-