## Sheet1
ISSUE # | TASK TITLE | USER STORY | STORY POINTS | DESCRIPTION / ASSOCIATED TASKS | DUE DATE | PRIORITY LEVEL(HIGH, MEDIUM, LOW) | RISK LEVEL (HIGH, MEDIUM, LOW) | RESPONSIBILITIES | SPRINT
#74 | Implement Self-Assessment Feature for Students Performance Evaluation | "As a student, I want to be able to assess myself and grade my performance on various criteria." | 3 | 1. self-assessment into assessment component 2. create a self-assessment button 3. update assessment dashboard to show self-assessments as well | 2024-11-26 | MEDIUM | MEDIUM | Hendrik, Jana, Yousef | 4
#75 | Enable commenting functionaliy for assessments | "As a teacher I would like to post comments to review student assessments." | 4 | 1. design comment section UI component 2. implement comment interaction 3. setup comment data model 4. create API for commenting and comment validation | 2024-11-27 | MEDIUM | MEDIUM | Hendrik, Jana, Yousef | 4